## Slide 1: Exchange 365 Hybrid Deployment: Test Strategy Plan and Acceptance Criteria

## Slide 2: Project Definition
This project aims to move our current on-premises Exchange to a Cloud system with MS 365.
Collaboration with NB Consult and SQ10 for setting up the Exchange Hybrid in line with Microsoft's guidelines.
Implementation of necessary network and firewall adjustments.
Migration of mailboxes and associated services.
Extensive testing to ensure deployment integrity.
Setup of Outlook Mobile for end-users via
Scope

## Slide 3: Wins (why are we doing this?)
Cost Efficiency
Scalability
Reduction in the cost of maintaining on-premises hardware and infrastructure.
Reliability and Uptime
Ability to easily scale the environment to meet changing business needs without significant additional investments.
Improved Collaboration
Enhanced collaboration features that come with cloud-based services like Microsoft 365.
Mobility and Flexibility
Allowing users to access their email and work collaboratively from any location and on any device.
Enhanced Security
Improved security features and compliance capabilities that are regularly updated in a cloud environment.
Higher reliability and better uptime statistics due to the distributed nature of cloud services.
Simplified IT Management
Reduced complexity in IT management and freeing up IT resources to focus on more strategic initiatives.
To ensure everyone understands the deployment steps, along with their respective roles and responsibilities, facilitating a smooth transition.

## Slide 4: Measurable Objectives
Ensuring a smooth transition between on-prem and Exchange.
Customizing settings for consistency with our current system.
Embracing 365's advanced features.
Simplifying configurations like databases and mailbox placements.
New features to optimize our email system and reduce disaster scenarios.

## Slide 5: Technical Setup: Before and After Transition
Before Transition
Exchange Server: On-premises servers handling email, calendars, contacts.
Active Directory (AD): For user identity management and authentication.
Local Data Storage: Emails and other data stored on-site.
After Transition to Microsoft 365 Hybrid Deployment
Exchange Online: Part of the cloud services for email, leveraging Microsoft's global infrastructure.
Network Infrastructure: Firewalls, load balancers, and VPNs for secure access.
Backup and Recovery Systems: On-premises solutions for data protection.
Azure Active Directory (AAD): Cloud-based identity and access management service, synced with on-premises AD for hybrid identity.
Cloud Storage: Data stored in Microsoft's data centers, offering high availability and disaster recovery capabilities.
Network Configuration: Adjustments to DNS, firewalls, and routing to support secure cloud connectivity.
Hybrid Configuration Wizard (HCW): Facilitates the integration of on-premises Exchange with Exchange Online, enabling seamless coexistence.
Security and Compliance: Enhanced through Microsoft 365's built-in security features, including Advanced Threat Protection (ATP), data loss prevention (DLP), and compliance standards support.

## Slide 6: Gate Checks: Activities, Deliverables, and Acceptance Criteria
Preparation Gate
Technical Setup Gate
Pilot Readiness Gate
Acceptance Criteria
Go-Live Gate
Acceptance Criteria
Acceptance Criteria
Deployment Gate
Acceptance Criteria
Successful hybrid environment setup
Network performance benchmarks met
Security standards compliance
Acceptance Criteria
Approval of infrastructure readiness
Stakeholder buy-in
Initial training framework
System stability
Positive feedback from pilot phases
Readiness of training materials
System performance meets or exceeds targets
Ability to scale as per demand
Operational support mechanisms.
No data integrity issues
System performing as expected
High user readiness level.
Activities | Status
Infrastructure Assessment | Pending
Stakeholder Alignment | Pending
Preliminary Training Plan | Pending
Deliverables | Status
Assessment Report | Pending
Stakeholder Engagement Plan | Pending
Training Outline | Pending
Activities | Status
Hybrid Configuration | Pending
Network Adjustments | Pending
Security Measures | Pending
Deliverables | Status
Configuration Document | Pending
Network Setup Report | Pending
Security Compliance Verification | Pending
Activities | Status
Pre-pilot Testing | Pending
Scalability Assessment | Pending
Support Setup | Pending
Deliverables | Status
Testing Reports | Pending
Scalability Analysis | Pending
Support Operational Plan | Pending
Activities | Status
Evaluation of pilot results | Pending
Final training materials | Pending
Performance optimization | Pending
Deliverables | Status
Evaluation Report | Pending
Training Materials | Pending
Performance Optimization Checklist | Pending
Activities | Status
Data Integrity Check | Pending
Performance Review | Pending
Readiness Assessment | Pending
Deliverables | Status
Data Integrity Report | Pending
Performance Report | Pending
System Readiness Report | Pending

## Slide 7: Pre-migration Checklist
Inventory of Existing Assets
Catalog all hardware, software, and network assets.
Analysis and Planning
Identify and categorize mailboxes and resources to be migrated.
Infrastructure Assessment
Assess current infrastructure for compatibility with cloud services.
User Communication
Develop a communication plan to inform users about the migration process and timelines.
Security and Compliance
Review security policies and compliance requirements.
Document current mailboxes, sizes, and usage statistics.
Establish migration batches and timelines.
Ensure network capacity for increased cloud traffic.
Update necessary hardware and software to meet prerequisites.
Prepare user guides and FAQs for reference.
Plan for any necessary changes in security posture.
Backup and Data Protection
Ensure all data is backed up and can be restored.
Test backup and restoration processes.
Third-Party Coordination
Coordinate with vendors and support teams for any integrated third-party applications.
Check for updates or patches required for compatibility.
Final Review and Approval
Conduct a final review of the migration plan with all stakeholders.
Obtain formal approval to proceed with the migration.
A general pre-migration checklist based on common practices for transitioning from an on-premises Exchange server to a cloud-based solution like Microsoft 365.

## Slide 8: Deployment Phases and Schedule
Note:
All dates are tentative and subject to change based on project progress and feedback.
Regular updates will be provided to keep everyone informed.
IT Alpha Phase
Focus: Technical Readiness
Status: Pending
IT Pilot
Focus: IT Testing
Business Pilot
Focus: User Testing
End Date: 09/02/24
Status: Pending
End Date: 09/02/24
Status: Pending
End Date: 09/02/24
Firmwide Release
Focus: Deployment Rollout
Status: Pending
End Date: 09/02/24

## Slide 9: IT Alpha Phase
Preliminary stage in the transition from on-premises Exchange to a cloud-based Microsoft 365 environment.
FOCUS : Establishing the technical foundation required for a smooth migration process.
Environment Assessment
Subtasks: <add total and a link to the list>
Owner: Malika
Hybrid Configuration
Status: Pending
Owner: Malika
Status: Pending
Subtasks: <add total and a link to the list>
Security and Compliance
Owner: Malika
Status: Pending
Directory Synchronization Setup
Subtasks: <add total and a link to the list>
Subtasks: <add total and a link to the list>
Owner: Malika
Status: Pending
Pilot Mailbox Migration
Subtasks: <add total and a link to the list>
Owner: Malika
Status: Pending
Acceptance Criteria
Successful Hybrid Setup: Verification that on-premises and cloud environments are correctly integrated and can coexist without issues.
Data Integrity: Confirmation that all migrated data is intact, with no loss or corruption.
Authentication and Connectivity: Ensuring users can authenticate and connect to their mailboxes seamlessly, regardless of their location (on-premises or cloud).
Security Compliance: All configurations must comply with organizational security standards and any applicable regulations.
Positive Feedback from Pilot Users: Feedback from users involved in the pilot migration should indicate a smooth transition experience, with minimal disruptions to their daily work.

## Slide 10: IT Alpha Phase - Tracker
Initial Testing with a Small, Controlled Group.
Gate Check |  |  | 
Item | Description | Status | Comments
Technical Setup | Ensure all necessary Cloud configurations and permissions are in place. | Pending | 
User Selection | Confirm the selection of a diverse group of users that represent a cross-section of the organization for the alpha test. | Pending | 
Pre-Migration Checklist | Complete a pre-migration checklist for each mailbox, ensuring data integrity and backup. | Pending | 
Health Check |  |  | 
Item | Description | Status | Comments
Migration Success Rate | Monitor and record the success rate of mailbox migrations, noting any errors or issues. | Pending | 
User Communication | Verify that users have received proper instructions and support documentation. | Pending | 
System Performance | Check the performance of the Cloud mail system for speed, delivery, and latency. | Pending | 

## Slide 11: IT Pilot
Comprehensive evaluation of the hybrid deployment in a controlled, yet realistic IT environment.
FOCUS : Validating the comprehensive functionality and integration of the new setup within a controlled environment before a broader rollout.
Extended User Testing
Subtasks: <add total and a link to the list>
Owner: Malika
Integration Testing
Status: Pending
Owner: Malika
Status: Pending
Subtasks: <add total and a link to the list>
Performance and Scalability Testing
Owner: Malika
Status: Pending
Security and Compliance Validation
Subtasks: <add total and a link to the list>
Subtasks: <add total and a link to the list>
Owner: Malika
Status: Pending
Acceptance Criteria
Successful User Experience: Participants report a positive experience with no significant disruptions to their workflow.
Integration Compatibility: All systems and applications interact without issues, maintaining data integrity and workflow efficiency.
Performance Benchmarks Met: The system meets predefined performance and scalability criteria, demonstrating readiness for a wider deployment.
Security and Compliance Approval: The deployment passes all security and compliance checks, with documented evidence of compliance.

## Slide 12: IT Pilot - Tracker
Broader Testing with the IT Department
Gate Check |  |  | 
Item | Description | Status | Comments
Alpha Feedback Incorporation | Implement changes based on feedback from the Alpha Pilot. | Pending | 
IT Readiness | Confirm that the IT team is prepared to support the migration and handle inquiries. | Pending | 
Security Measures | Ensure all security protocols are in place and functioning as expected. | Pending | 
Health Check |  |  | 
Item | Description | Status | Comments
IT Feedback | Gather and assess feedback from the IT department on migration process, system performance, and any encountered issues. | Pending | 
Support Request Analysis | Analyze support requests to identify common issues or trends that need addressing. | Pending | 
Access and Security Testing | Conduct thorough testing of access controls and security measures post-migration. | Pending | 

## Slide 13: Business Pilot
Evaluating the cloud-based system's performance from a business operational perspective, ensuring it meets the practical needs of the end-users and integrates seamlessly into daily workflows.
FOCUS : Ensuring the deployment not only meets technical specifications but also aligns with and supports the organization's business objectives, paving the way for a successful organization-wide rollout.
Subtasks: <add total and a link to the list>
Owner: Malika
Real-World Scenario Testing
Status: Pending
Owner: Malika
Status: Pending
Subtasks: <add total and a link to the list>
Feedback Collection and Analysis
Owner: Malika
Status: Pending
Adjustment and Optimization
Subtasks: <add total and a link to the list>
Subtasks: <add total and a link to the list>
Owner: Malika
Status: Pending\
Business User Involvement
Acceptance Criteria
Positive User Feedback: The majority of business users report satisfaction with the system's performance and usability in their daily tasks.
Efficiency and Productivity Gains: Demonstrated improvements in task efficiency or productivity, indicating that the new system supports business operations effectively.
Issue Resolution: Any issues identified during the pilot are successfully resolved without significant impact on business processes.
Business Process Integration: Seamless integration of the cloud system into existing business processes, with minimal disruption and high adoption rates.

## Slide 14: Business Pilot - Tracker
Targeted Rollout to Business Services Departments
Gate Check |  |  | 
Item | Description | Status | Comments
IT Pilot Learnings | Apply lessons learned and improvements from the IT Pilot phase. | Pending | 
Business Impact Assessment | Evaluate potential impacts on business operations and ensure mitigation strategies are in place. | Pending | 
Training and Documentation | Confirm that targeted training sessions and updated documentation are available for Business Services users. | Pending | 
Health Check |  |  | 
Item | Description | Status | Comments
Operational Impact | Monitor the operational impact on Business Services, ensuring that there are no disruptions to daily activities. | Pending | 
User Satisfaction | Survey users to assess satisfaction with the migration process and Cloud mailbox functionality. | Pending | 
Compliance and Data Integrity | Verify compliance with regulatory requirements and check for any issues with data integrity post-migration. | Pending | 

## Slide 15: Firmwide Release
The final phase in the deployment process, marking the transition to the cloud-based system across the entire organization.
FOCUS : Ensuring the cloud-based system is fully integrated into the organization's operations, providing a modern, scalable, and efficient communication and collaboration platform.
Subtasks: <add total and a link to the list>
Owner: Malika
Final User Training and Support
Status: Pending
Owner: Malika
Status: Pending
Subtasks: <add total and a link to the list>
Monitoring and Optimization
Owner: Malika
Status: Pending
Subtasks: <add total and a link to the list>
Full-Scale Deployment
Acceptance Criteria
Successful Migration: All mailboxes and data are successfully migrated to the cloud without loss of information or significant downtime.
User Adoption: High rate of user adoption, with positive feedback on the ease of use and benefits of the new system.
Operational Continuity: The organization's operations continue smoothly during and after the migration, with no significant impact on business processes.
Performance and Reliability: The system meets or exceeds the expected performance and reliability standards, supporting the organization's needs effectively.

## Slide 16: Firmwide Release - Tracker
Final Rollout to the Entire Organization
Gate Check |  |  | 
Item | Description | Status | Comments
Preparation of Findings | Review and incorporate findings from previous pilots to refine the migration strategy. | Pending | 
Full-Scale Deployment Plan | Ensure a comprehensive deployment plan is in place, including timelines, user communication, and support. | Pending | 
Training and Support Readiness | Confirm that training materials are updated and support teams are ready for firmwide rollout. | Pending | 
Health Check |  |  | 
Item | Description | Status | Comments
Deployment Monitoring | Closely monitor the migration process for any issues or delays, implementing real-time adjustments as needed. | Pending | 
System Stability and Performance | Assess the stability and performance of the Cloud system under full load conditions. | Pending | 
Feedback and Resolution | Establish a feedback loop with users to quickly identify and resolve any issues arising from the firmwide rollout. | Pending | 

## Slide 17: Integrations
Testing Schedule for Exchange-Integrated Applications.
FOCUS : Ensuring robust compatibility and peak performance, guaranteeing a streamlined experience for all our users.
App | Owner | Migration Phase | Status | Comments
CiscoWebex Calendar Service | Andrew M | IT Pilot | Pending | 
CodeTwo | Scott | NA | Pending | 
Hoxhunt Outlook Add-in | Tash | NA | Pending | 
InteractionSync | Hasan | UAT | Pending | 
Proofpoint ContinuityExchImpersonator (Calendar/Contact Sync) | Scott | NA | Pending | 
ProofpointTrap | Scott | NA | Pending | 
Rendezvous | Hasan | IT Pilot | Pending | 
Rubrik Backups | John | UAT | Pending | 
IntApp_Impersonation | Ricky McNair | NA | Pending | 
Veronis | Rob Welch | NA | Pending | 
ePDF | Galina | NA | Pending | 
EU BlackBerry Server | NA | NA | Pending | 
Mailbox Search-vmwareadmin | NA | NA | Pending | 
Mailbox Search-zzsolarwinds | Jim Barnabei | NA | Pending | 
US BlackBerry Server | NA | NA | Pending | 
Hubspot | Scott | NA | Pending | 
WorksiteImpersonation2013 | NA | NA | Pending | 
WorksiteImpersonationLO | NA | NA | Pending | 

## Slide 18: Testing Criteria
Units: <add total and a link to the list>
Owner: Malika
Final User Training and Support
Status: Pending
Owner: Malika
Status: Pending
Units: <add total and a link to the list>
Monitoring and Optimization
Owner: Malika
Status: Pending
Units: <add total and a link to the list>
Full-Scale Deployment
Inclusions
Functionality Testing: Ensures all features work as expected in the cloud environment.
Performance Testing: Assesses the system's responsiveness, stability, and scalability post-migration.
Security Testing: Verifies that security measures are effective and data integrity is maintained during and after migration.
Compatibility Testing: Checks that the new system works seamlessly with existing applications and services.
Unit Testing

## Slide 19: Testing Checklist and Schedule
Note:
All dates are tentative and subject to change based on project progress and feedback.
Regular updates will be provided to keep everyone informed.
Functionality Testing
Focus: Feature testing
Status: Pending
Performance Testing
Focus: System's responsiveness, stability, and scalability post-migration.
Security Testing
Focus: Security measures and data integrity
End Date: 09/02/24
Status: Pending
End Date: 09/02/24
Status: Pending
End Date: 09/02/24
Compatibility Testing
Focus: Integration testing
Status: Pending
End Date: 09/02/24
Pre-Migration
Post-Migration
Backup data
Confirm migration paths
Prepare user communication
Conduct thorough user acceptance testing
Gather feedback
Provide training and support
During Migration
Monitor data transfer processes
Validate data integrity
Test key functionalities
Checklist

## Slide 20: Outlook Mobile Testing Criteria
Inclusions
Functionality Testing: Verification of core features such as email sending/receiving, calendar entries, and contact synchronization.
User Interface and Experience: Ensuring the app's interface is user-friendly and consistent with desktop versions.
Connectivity and Performance: Testing the app's performance over various network conditions and its ability to handle synchronization without excessive battery drain.
Security Testing: Confirming that the app complies with corporate security policies and data protection standards.
Post-Migration
Backup data
Confirm migration paths
Prepare user communication
Conduct thorough user acceptance testing
Gather feedback
Provide training and support
During Migration
Monitor data transfer processes
Validate data integrity
Test key functionalities
Pre-Migration
Checklist
Functionality Testing
Focus: Feature testing
Status: Pending
UI Testing
Focus: User Interface.
Performance Testing
Focus: Performance and connectivity
End Date: 09/02/24
Status: Pending
End Date: 09/02/24
Status: Pending
End Date: 09/02/24
Security Testing
Focus: Security measures and data integrity
Status: Pending
End Date: 09/02/24
Units: <add total and a link to the list>
Owner: Malika
Offline Access
Status: Pending
Owner: Malika
Status: Pending
Units: <add total and a link to the list>
Notifications
Owner: Malika
Status: Pending
Units: <add total and a link to the list>
Setup and Configuration
Integration with Phone Features
Units: <add total and a link to the list>
Owner: Malika
Status: Pending
Unit Testing

## Slide 21: Outlook Mobile Configuration - Tracker
Final Rollout to the Entire Organization
Gate Check |  |  | 
Item | Description | Status | Comments
Technical Setup | Ensure all necessary Cloud configurations and permissions are in place. | Pending | 
User Selection | Confirm the selection of a diverse group of users that represent a cross-section of the organization for the alpha test. | Pending | 
Pre-Migration Checklist | Complete a pre-migration checklist for each mailbox, ensuring data integrity and backup. | Pending | 
Health Check |  |  | 
Item | Description | Status | Comments
Migration Success Rate | Monitor and record the success rate of mailbox migrations, noting any errors or issues. | Pending | 
User Communication | Verify that users have received proper instructions and support documentation. | Pending | 
System Performance | Check the performance of the Cloud mail system for speed, delivery, and latency. | Pending | 

## Slide 22: Go Live Checklist
User Communication Plan Implemented
All users are informed about the migration schedule and what to expect.
Mobile and Desktop Client Connectivity
All clients can connect to the new cloud environment.
Full Data Backup Comprehensive backups completed and verified to ensure data can be restored if necessary.
System Health Check
All systems operational with no critical issues pending.
Security Clearance
Security protocols tested and in place.
Mail Flow Tests Completed
Internal and external mail flow confirmed to be working correctly.
User Training Completed
All clients can connect to the new cloud environment.
Support Teams Ready Support teams are prepared to handle inquiries and issues.
Final Sign-Off All stakeholders have reviewed and approved the migration for go-live.

## Slide 23: Known Issues and Resolution Plan
Note:
Remember, each of these issues will be resolved as we move forward with our MS 365 Hybrid Deployment, making our email system more efficient and user-friendly.
Large Mailboxes
Issue: Managing large mailboxes can be challenging.
Resolution: Implement email archiving in MS 365 to manage and reduce mailbox sizes efficiently.
Physical Server Reliance
Issue: High maintenance for physical servers and storage.
Resolution: Transition to MS 365 reduces the need for on-prem servers, cutting down maintenance and costs.
Database and Mailbox Placement Management
Issue: Current on-prem setup requires extensive configuration management.
Resolution: MS 365 simplifies mailbox management, reducing the need for complex configurations.
Disaster Recovery
Issue: Potential for site downtimes and data loss.
Resolution: MS 365 offers robust backup and recovery options, decreasing disaster scenarios.
Introducing New Features
Issue: Adapting to and leveraging new features can be challenging.
Resolution: Provide comprehensive training and support for new features like Advanced Threat Protection and FIND TIME.
Status: Pending
Owner: Malika
Status: Pending
Owner: Malika
Status: Pending
Owner: Malika
Status: Pending
Owner: Malika
Status: Pending
Owner: Malika

## Slide 24: Training
Training will be a systematic process tailored to ensure a smooth transition for all users.
FOCUS: To equip users with the knowledge and skills necessary to navigate the new cloud environment efficiently and confidently.
Plan
Scheduled Sessions: Training sessions will be scheduled in advance, timed to follow the migration phases to reinforce learning.
Training Formats: A mix of live webinars, recorded tutorials, and interactive Q&A sessions.
Resource Availability: Comprehensive guides, FAQs, and cheat sheets will be made available on the company intranet.
Hands-on Workshops: Practical workshops for users to familiarize themselves with the new system.
Support Teams: Designated support personnel will assist with hands-on help post-training.
Feedback Mechanisms: Post-training surveys to gather feedback and identify areas needing additional support.

## Slide 25: Technical set up: Considerations
Hybrid deployment requirements:
Before we configure a hybrid deployment, we need ensure on-premises organization meets all of the prerequisites required for a successful deployment.
Exchange ActiveSync clients:
When we move a mailbox from on-premises Exchange organization to Exchange Online, all of the clients that access the mailbox need to be updated to use Exchange Online; this includes Exchange ActiveSync devices. Most Exchange ActiveSync clients will now be automatically reconfigured when the mailbox is moved to Exchange Online, however some older devices might not update correctly.
Mailbox permissions migration:
On-premises mailbox permissions such as Send As, Full Access, Send on Behalf, and folder permissions, that are explicitly applied on the mailbox are migrated to Exchange Online. Inherited (non-explicit) mailbox permissions and permissions granted to objects that aren't mail enabled in Exchange Online are not migrated.
Support for cross-premises mailbox permissions:
Mailbox forwarding settings:
Exchange hybrid deployments support the use of the Full Access and Send on Behalf Of permissions between mailboxes located in an on-premises Exchange organization and mailboxes located in Exchange Online. Additional steps are required for Send As permissions. Also, some additional configuration may be required to support cross-premises mailbox permissions depending on the version of Exchange installed in your on-premises organization
Mailboxes can be set up to automatically forward mail sent to them to another mailbox. While mailbox forwarding is supported in Exchange Online, the forwarding configuration isn't copied to Exchange Online when the mailbox is migrated there. Before we migrate a mailbox to Exchange Online, ensure to export the forwarding configuration for each mailbox

## Slide 26: Technical setup
Microsoft Exchange Management Shell (EMS)
Office 365 Admin Portal
Test user accounts
Migration tools (if applicable)
User feedback forms
Connectivity test tools (Ex: Microsoft Test Connectivity)
Mobile device management (MDM) solution (optional)
Tools and Resources

## Slide 27: Wins why we are doing this
Secure mail routing between on-premises and Exchange Online organizations.
Mail routing with a shared domain namespace. For example, both on-premises and Exchange Online organizations use the @contoso.com SMTP domain.
A unified global address list (GAL), also called a "shared address book."
Free/busy and calendar sharing between on-premises and Exchange Online organizations.
Centralized control of inbound and outbound mail flow. You can configure all inbound and outbound Exchange Online messages to be routed through the on-premises Exchange organization.
A single Outlook on the web URL for both the on-premises and Exchange Online organizations.
The ability to move existing on-premises mailboxes to the Exchange Online organization. Exchange Online mailboxes can also be moved back to the on-premises organization if needed.
Centralized mailbox management using the on-premises Exchange admin center (EAC).
Message tracking, MailTips, and multi-mailbox search between on-premises and Exchange Online organizations.
Cloud-based message archiving for on-premises Exchange mailboxes. Exchange Online Archiving can be used with a hybrid deployment.
Benefits

## Slide 28: Outlook mobile Testing and checklist
Goal
Testing Methodology
Testing Devices
Ensure seamless email, calendar, contacts, and collaboration access through Outlook mobile for all users transitioning to your hybrid Exchange 365 environment
Black-box: Focus on real-world user workflows and functionalities.
Include diverse Android and iOS devices representative of your user base.
White-box: Verify technical configuration and data synchronization.
Consider different screen sizes, operating system versions, and network conditions (Wi-Fi, cellular).

## Slide 29: Outlook mobile Testing and checklist
Basic Functionality
Account setup and access: Verify smooth initial setup with existing user credentials.
Advanced Features
Push notifications: Verify timely delivery of email, calendar, and contact updates.
Security and Performance
Multi-factor authentication (MFA): Test seamless integration and user experience with MFA prompts.
User Experience
Usability: Assess intuitiveness of the interface, ease of navigation, and clarity of actions.
Email: Test sending, receiving, searching, deleting, and managing attachments.
Calendar: Check event creation, editing, deletion, syncing, and reminders.
Contacts: Ensure contact creation, editing, searching, and syncing across devices.
Offline access: Test email functionality and limited calendar/contact access without internet connection.
Search: Evaluate search accuracy and speed for emails, calendars, and contacts.
Meetings and Teams: Test joining, scheduling, and participating in meetings within Outlook mobile.
Attachments: Verify opening, saving, and sharing of various file types.
Conditional Access: Ensure compliance with organizational security policies on mobile devices.
Performance: Measure app launch times, screen transitions, and responsiveness under different network conditions.
Battery consumption: Monitor battery usage and identify any excessive drain related to Outlook mobile.
Accessibility: Verify compatibility with assistive technologies for users with disabilities.
Localization: Test functionality and user interface elements in relevant languages, if applicable.

## Slide 30: Go live checklist
Basic Functionality
Create Microsoft 365 mailboxes for both new and existing users, utilizing Exchange Admin Center or Exchange Management Shell.
Verify Global Address List (GAL) Visibility
Draft emails from both on-premises and Office 365 user mailboxes in Outlook.
Shared Mailbox Access and Hybrid Mail Flow
Confirm visibility of the Shared Mailbox in both on-premises Exchange and Office 365 using EAC.
Send-on-Behalf
Assign permissions for Send-on-Behalf and Delegate Access.
.Assign Exchange Online licenses and synchronize users to Office 365 using Azure AD Connect.
Test email flow by sending messages between on-premises and Office 365 mailboxes.
Confirm successful mail flow from Office 365 to on-premises and vice versa.
Ensure external mail flow by sending test emails to and from external email servers like Gmail or Hotmail.
Confirm visibility of users from both on-premises Exchange and Office 365 in the GAL list for on-premises and Office 365 user mailboxes
Test mail flow to Shared Mailbox by sending emails from both on-premises and Office 365 user accounts in Outlook.
Receive delivery receipts in on-premises Exchange and Office 365 user's Outlook Inbox, confirming functional hybrid mail flow to the Shared Mailbox.
Verify Send-on-Behalf or Send As capabilities by drafting an email in Outlook from an Office 365 user mailbox.
Confirm the ability to Send As or Send on Behalf of a group or user.
Check delegate access by accessing and modifying the assigned user's calendar from your Office 365 account.
Perform tests to create new events, meetings, or appointments in the user's calendar to ensure delegate access is functional.
Test ActiveSync by signing in to the Outlook client on Android or iOS smartphones.
Send a test email from Office 365 or on-premises Exchange user's account to on-premises and external email servers, such as Gmail.

## Slide 31: Applications Test checklist
8. Rendezvous
7. Rubrik Backups
8. IntApp_Impersonation
10. ePDF
9. Veronis
🎯Assigned To: Hasan
🎯Assigned To: John
🎯Assigned To: Ricky McNair
🎯Assigned To: Rob Welch
🎯Assigned To: Galina

## Slide 32: Applications Test checklist
11. Mailbox Search-vmwareadmin
12. Mailbox Search-zzsolarwinds
13. ProofpointTrap
15. WorksiteImpersonation2013/O
14. Hubspot
🎯Assigned To: Gary Wotring
🎯Assigned To: Jim Barnabei
🎯Assigned To: Scott
🎯Assigned To: Scott
🎯Assigned To: Laura Anglum

## Slide 33: Test Strategy - Overview
Purpose of Testing
How We Test
Key Testing Components
Success Measure
Testers Involved
🎯Ensure Flawless Functionality: Make sure our MS 365 Hybrid Deployment is successful.
🐞 Find and Fix Problems: Catch any issues before everything is finalized.
📅 In Phases: Test different parts step-by-step to ensure smooth integration.
🌍 Real-Life Scenarios: Use real examples to guarantee practical usability.
🔁 Feedback Loop: Incorporate feedback for continuous improvement.
📬 Mailbox Migration: Verify the seamless transfer of mailboxes to MS 365.
🔒 Network and Firewall Settings: Ensure technical configurations are precise for secure and uninterrupted email flow.
🔗 Integration with Current Systems: Confirm that MS 365 harmonizes with our existing infrastructure.
💡 Tech Experts: <add names>
👥 End Users: <add names>
✅ Seamless Operation: Aim for a smooth transition so users feel no disruption, only enhancement with MS 365 features.

## Slide 34: Acceptance Criteria for a Seamless Transition
Successful Mailbox Migration
Seamless Mailbox Operation
Every mailbox should transfer smoothly from on-prem to MS 365 without data loss.
Users should not notice any changes in their email functionality.
Optimized Mailbox Management
Migrated mailboxes must work like they did before - emails, calendar invites, and contacts should behave as usual.
Internal emails should act as if they are within the same system, ensuring privacy and security.
No External Email Disruption
Emails to and from outside the organization should continue without any hiccups.
All external communication routes (inbound and outbound) must remain the same, ensuring business continuity.
Meeting Microsoft Standards
Our setup must follow Microsoft's guidelines for a Hybrid deployment.
This ensures we get the best out of the system and avoid potential issues.
Effective Training & Clear Documentation
FF Helpdesk team must be fully trained to handle the new system.
Documentation should be clear, helping with common questions and guiding through usual tasks.
The new system should help us manage large mailboxes better, making our email system more efficient.
We aim to reduce our reliance on physical servers, saving space and resources.
Positive Feedback
After migration, we need good feedback from users, showing that the system works well and meets their needs.
We'll measure success through fewer complaints, quicker response times, and positive user surveys.

## Slide 35: Project Risks and How We Handle Them
Note:
Each point addresses a potential risk by clearly stating the risk and immediately following up with a straightforward, understandable mitigation strategy. This approach keeps the information accessible and actionable.
Email Access During Migration
What it means: You might have short breaks accessing your emails when we move them.
Outlook Connection
What it means: Outlook might disconnect and ask you to restart at the end of moving your mailbox.
Surprises After Moving
What it means: After we move mailboxes, unexpected issues from other apps you use might pop up.
How we handle it: We'll move emails when you're less likely to need them. We'll sync mailbox moves with delegate access to reduce issues.
How we handle it: We'll let you know this might happen. It's a quick fix – just a restart of Outlook.
How we handle it: We're ready to fix these surprises. If needed, we can move your mailbox back, but we'll try to solve it first.
Email Access for Clients
What it means: Clients might have a short break in email access because of when their mailbox moves.
How we handle it: We'll plan mailbox moves carefully, especially for clients, to ensure it's smooth. We'll do the big moves when it's least likely to interrupt your work.

## Slide 36: Interdependencies
Summary:
Our project's success depends on working closely with different teams and projects. Understanding and managing these interdependencies ensures a seamless and efficient transition to our new system.
Security Collaboration
Integration with Intune Project
Testing and Backup Preparations
Handling Large Mailboxes
Team Coordination
Security is a top priority.
Continuous collaboration with the security team throughout the project.
Our work goes hand-in-hand with the Intune project.
Ensure both projects align for a smooth transition.
Developing strategies for large mailbox migration.
Includes archiving solutions as part of the process.
Close coordination is needed between Network, Applications, and Active Directory teams.
Ensures smooth project progression without delays.
Implement strong backup solutions for data safety.
Before moving mailboxes to the cloud, thorough testing is crucial.

## Slide 37: Impact on Users
Note:
We understand the importance of every user in this transition and are committed to ensuring a positive experience for all.
All Users Affected
Smooth Transition
Benefits
Training & Communication
Every user will experience changes as we shift mailboxes to the cloud.
New mailboxes will also be created directly in the cloud.
We aim for a seamless transition with minimal disruptions.
Support will be available to guide users through the new setup.
Training materials and sessions will be provided to help users adapt.
Helpdesk will be equipped to handle queries and provide assistance.
Regular updates will be shared to keep everyone informed.
Feedback channels will be open for questions and concerns.
Enhanced features and improved mailbox management.
Access to new tools like Advanced Threat Protection and FIND TIME.

## Slide 38: Success Criteria
Smooth Transition for Users
Users won't notice the change. Their emails, calendars, and contacts work just like before.
Following the Rules
We stick to Microsoft's playbook for setting everything up. No shortcuts.
Everyone Knows What to Do
We train our Helpdesk team well. They'll have guides to help users move their mailboxes without a hitch.
We'll Check and Double-Check
After we're done, we'll ask you how it's going and measure everything to make sure it's better, safer, and everyone's happy.
Emails Flow as Usual
External emails? No problem. They'll keep coming and going, business as usual.
Better Mailbox Management
We'll use less space in our office for servers. Big mailboxes get trimmed down, making everything neater and more organized.

## Slide 39: Conclusion and Next Steps
Recap of Key Points
Next Steps
Your Role
We are transitioning to a hybrid MS 365 setup, aiming for seamless integration and optimized mailbox management.
Our strategy involves thorough testing at each phase to ensure a smooth transition.
We are aware of the risks and have plans in place to mitigate them effectively.
Finalize Test Strategy: Ensure our testing plan is comprehensive and covers all critical components.
Communicate with Stakeholders: Keep everyone informed about the project's progress and what to expect next.
Schedule Next Review Meeting: Set a date for the next project review to discuss progress and address any concerns.
Stay Informed: Keep up with updates and share any feedback or concerns.
Be Prepared: Understand the changes that are coming and how they will affect your work.
Support the Transition: Be ready to adapt to the new system and help others do the same.
Remember:
This transition is a team effort, and every single contribution is valuable in making this shift successful and beneficial for all of us.

## Slide 40: Q&A
Have Any Questions?
We're here to help clear up any queries or concerns you might have! Feel free to ask about:
Project Details: Need more info on specific parts of the project?
Test Strategy: Wondering how we'll ensure everything works smoothly?
Risks & Solutions: Worried about potential hiccups? Let's talk about our safety nets!
Next Steps: Curious about what happens after this meeting?
Your Thoughts Matter!
Your feedback, ideas, and insights are crucial for our success. If there's anything on your mind, now's the time to share!